## Sheet1
Project Work Breakdown Structure
Stage | Step | Detail | Description | Start | End | Total Time (Days) | Assigned
| 1 |  | Plan roles and schedule | 2016-01-11 | 2016-01-11 | 1 | Group Colab
| 2 |  | 4 parts
Prototype 1 Stage of Project | 2.1 | Part 1 |  | 2016-01-12 | 2016-02-08 | 21
| 2.1.1 | Step 1 | Come up with idea and basic interface of website (also assign specific protoype 1 tasks) | 2016-01-12 | 2016-01-12 | 1 | Group Colab
| 2.1.2 | Step 2 | Dmitrii and KP will begin design of the database for the website | 2016-01-13 | 2016-01-18 | 5 | Dmitrii, KP
|  |  | Justin will work on prototype 1 presentation along with starting leadership project journal | 2016-01-13 | 2016-01-18 | 5 | Justin
|  |  | Amir will begin trying to add some CSS to the interface of the website | 2016-01-13 | 2016-01-18 | 5 | Amir
| 2.1.3 | Step 3 | Meet during the 2 work periods during the week and put all content together, check in with each other as well as come up with potential questions | 2016-01-18 | 2016-01-22 | 4 | Group Colab
| 2.1.4 | Step 4 | Meeting at Dmitriis residence and enjoying some team bonding and touching base with the completion of protoype 1, brainstorm potential questions | 2016-01-22 | 2016-01-22 | 1 | Group Colab
| 2.1.5 | Step 5 | Try to complete majority of protoype 1 for meeting with Dave and Peter:
|  |  | Amir continue on updated design and take input from others to create almost complete design for review meeting 1 | 2016-01-23 | 2016-01-25 | 3 | Amir
|  |  | Justin continue to put presentation together and complete the presentation before review meeting 1 so there is practise time, also submit journal by Sunday | 2016-01-23 | 2016-01-25 | 3 | Justin
|  |  | KP and Dmitrii continue on with database design and figure out how to effectively create the tables | 2016-01-23 | 2016-01-25 | 3 | Dmitrii, KP
| 2.1.6 | Step 6 | Meet with Dave and Peter and take the information given to make a very effective looking prototype 1 | 2016-01-25 | 2016-01-25 | 1 | Group Colab
| 2.1.7 | Step 7 | Take the information and feedback given at the review meeting and work throughout the week on creating an even better completed prototype | 2016-01-26 | 2016-01-29 | 3 | Group Colab
Weekend Break
| 2.1.8 | Step 8 | Take the updated presentation and prototype and practise all week until the presentation is flawless | 2016-02-01 | 2016-02-05 | 5 | Group Colab
| 2.1.9 | Step 9 | Continue to practise working on the presentation and fix last minute details, enjoy the weekend but still practise | 2016-02-05 | 2016-02-08 | 1 | Group Colab
| 2.1.10 | Step 10 | Present prototype 1 to the client | 2016-02-08 | 2016-02-08 | 1 | Group Colab
Prototype 2 Stage of Project | 2.2 | Part 2 |  | 2016-02-09 | 2016-03-14 | ~25
| 2.2.1 | Step 1 |  | 2016-02-09
Prototype 3 Stage of Project | 2.3 | Part 3 |  | 2016-03-15 | 2016-04-04 | 21
| 2.3.1 | Step 1
Final Project | 2.4 | Part 4 |  | 2016-04-05 | 2016-04-18
| 2.4.1 | Step 1